## LSST Timeline
Vera C. Rubin Observatory (LSST) — Project Timeline
Legacy Survey of Space and Time ¦ Cerro Pachón, Chile ¦ 2015 – 2035
Year / Period | Status | Phase | Milestone | Description | Duration | Notes
2015 | ✅ Complete | Construction | Groundbreaking | Construction officially began on Cerro Pachón in Chile. | — | Elevation: 2,682 m above sea level
2019 | ✅ Complete | Integration | M1M3 Mirror Integration | The 8.4-metre primary/tertiary mirror (M1M3) integrated with the telescope mount assembly. | ~4 years | Largest monolithic mirror of its kind
2021 | ✅ Complete | Integration | M2 Mirror Installation | Installation of the secondary mirror (M2) and its cell assembly. | ~2 years | 62 cm diameter convex mirror
2023 | ✅ Complete | Integration | LSST Camera Integration | Integration of the 3.2-gigapixel LSST Camera — the largest digital camera ever built. | ~2 years | 189 sensors; 3,200 megapixels
Late 2024 / Early 2025 | 🔵 Projected | Commissioning | First Light | First Light with the full system and beginning of science verification phase. | ~6 months | Full system end-to-end test
Late 2025 | 🔵 Projected | Survey Start | LSST Survey Commences | Commencement of the 10-year Legacy Survey of Space and Time (LSST). | 10 years | Will map ~20 billion galaxies
2035 | 🔵 Projected | Survey End | Primary Survey Completion | Completion of the primary 10-year survey; data release and legacy archive. | — | ~500 PB of data expected

## Summary & Stats
LSST Project — Key Statistics
Metric | Value | Unit | Notes
Primary Mirror Diameter | 8.4 | metres | Combined M1/M3 monolithic mirror
Camera Resolution | 3,200 | megapixels | Largest digital camera ever built
Camera Sensors | 189 | CCDs | 4k × 4k each
Survey Duration | 10 | years | Starting late 2025
Sky Coverage per Visit | 9.6 | deg² | Field of view
Revisit Cadence | ~3–4 | nights | Same sky patch
Total Data Volume | ~500 | petabytes | Full 10-year survey
Galaxies Catalogued (est) | ~20 | billion | Projected galaxy count
Telescope Altitude | 2,682 | metres | Cerro Pachón, Chile
Total Project Duration | 20 | years | 2015 construction → 2035 survey end